## Sheet1
SI.No | Activity | Responsibility | Time Line
1 | Identification of Beneficiary, Households for High Cluster | Prani Mitra/Mastya Mitra,BLC,BPM,YP | Latest by 30th April | SoP Preparation
2 | Identification of Ponds for rolling out of Pisciculture Cluster as per the guideline | Prani Mitra/Mastya Mitra,BLC,BPM,YP | Latest by 15th May | Vetting of SoP
3 | Pisciculture Mapping to be done in the Cluster | DMMU,BMMU, and Community Cadres | Latest by 15th May | District Orientation
4 | Sharing of Households,SHGs and Beneficiary details to DMMU and SMMU | BMMU and GPLF | Latest by 30th May
5 | Proposal preparation and submission to BMMU by GPLF | BMMU and GPLF | Latest by 15th Jun
6 | Approval of proposal from Technical team at BMMU and suitable convergence with MGNREGS,Fishery Dept and other line department | BMMU | Latest by 15th Jun
7 | Updatation of MPR with Cluster formation and establishment | DMMU and BMMU | Latest by 30th July
8 | Proposal review and budget approval at DMMU | DMMU | Latest by 30th July
9 | Releasing of Fund to Clusters through GPLF |  | Latest by 15th August
10 | Preliminary Meeting and Orientation | DPM,BPM and SMMU Officials | Latest by 15th August
11 | Training on Pisciculture Clusters to the Beneficiaries and BMMU Staff and Action Plan Preparation | DMMU Officials,Asst.Fisheries Officers,BTM,ATMA and Other Line Department Officials as per the need | Latest by 15th August
12 | Dyke Preparation ,Pond Management and Bio-Security Measures | DMMU,BMMU | Latest by 30th August
13 | Procurement of Inputs (All inputs required for establishment ) | DMMU,BMMU | Latest by 30th August
14 | Supplementary Feeding up to harvesting | DMMU,BMMU | 1st Week Onwards up to 3 Months for Fry to Fingerlings and 9 Months from Fingerlings to Fully Grown
15 | 2nd Refresher Training-cum-Exposure Visit | SMMU,DMMU,BMMU | End of Each Season

## Organic
NTFP Cluster Timeline for State | Date (Approximate)
SoP Preparation of NTFP Cluster | 16th September, 2021
Approval for Van Mitra/Van Sakhi and Peparation of selection protocol of Van Mitra/ Van Sakhi | 20th September
Vetting by competent Authority | 23th September
Letter to districts for Selection of Blocks, potential NTFP products and selection of Van mitra/Van Sakhi | 26th September
Approval by competent authority for selection of Blocks | 28th September
District Orientation regarding action plan for upcoming season | 30th September
Beneficary selection | 1st October
Letter to all Line Departments (TDCC, Forest department etc) for kind information | 4th October
Sustainable collection training to all beneficaries for upcoming season | 4th October onwards
1st Monthly Review Meeting | Last week of October
Meeting with DPMs with presence of higher competent authority to discuss about constraints faced by beneficaries in 1st month | 1st week of November

## Montoring Format
Monitoring Format for NTFP Clusters
Sl No. | Name of District | Name of Block | Name of the Van Mitra/Van Sakhi | Contact No. of Van Mitra/Van Sakhi | No. of Beneficaries | No. of PGs | No. of SHGs | Name of NTFP products | Quantities Collected (in KGs) | Market Linkage (Yes/No) | Total Sales Cost | Average Income per HH
1
2
3
4
5

## Floriculture
Floriculture | Responsibility | Timelines
Vetting of SoP | YP(Floriculture) | 15th September
Orientation with District | YP(Floriculture) | 17th September
SoP sharing with District | YP(Floriculture) | 20th September
Identification of beneficiaries for floriculture cluster | BLC,BPM,YP | 24th September
Training on Floriculture cluster with the help of KVKs, RSETII,line department | DPM,RSETII,KVK | 28th September
Patch Identification for floriculture cluster | BPM,BLC,YP | 24th September
Sharing of HH details of beneficiaries with DMMU & SMMU | BPM,BLC,YP | 30th September
Proposal preparation & submission to BMMU by GPLF | BPM,BLC,YP | 1st October
Approval of proposal from line department for possible conververgence | DPM,BPM | 5th October
MPR updation regarding Floriculture Cluster | District MIS person | 5th October
Fund release to cluster from GPLF | DPM,BPM | 7th October
Procurement of inputs as per guideline | BPM,BLC,YP,MBK | 16th October
Field preparation & planting of saplings | Benificiary | 21th October
Interculture operation management | Benificiary | 5th November

## Spawn Unit
Spawn Production Unit | Responsibility | Timelines
Orientation with District | YP(Pathology) | 17th September
Identification of beneficiaries for Spawn production Unit | Krushi Mitra,BLC,BPM,YP | 20th September
Training on Spawn production with the help of KVKs, RSETII,line department | DPM,RSETII,YP | 29th September
Site for establishment of Spawn Production Unit | BLC,BPM,YP | 1th October
Sharing of SHG details with DMMU & SMMU | District MIS portion | 4th October
Proposal preparation & submission to BMMU by GPLF | MBK,BLC,YP | 8th October
Approval of proposal from line department for possible conververgence | DPM,BPM | 11th October
MPR updation regarding Spawn production Unit | District MIS person | 11th October
Fund release to cluster from GPLF | DPM,BPM | 16th October
Procurement of equipements as per guideline | BPM,BLC,YP | 21st October
Equipement setup with the help of technician | BPM,BLC,YP | 22nd October
First Batch Spawn Production | Cluster member | 22nd November

## Organic Cluster
Organic Clusters | Resposibility | Timelines
Vetting of SoP | YP(Organic) | 25th September
SoP sharing with District | YP(Organic) | 28th September
District Orientation regarding action plan for next season | PM(Agriculture) | 28th September
Identification of beneficiaries for Organic cluster | BPM,BLC,YP | 9th October
Patch Identification for Organic Cluster | BPM,BLC,YP | 9th October
Pre season Crop planning meeting & Crop identification with support of Service provider & RC | BPM,BLC,YP,RC,Service Provider | 1st Fortnignt of November
Documentation of group members as per APEDA norm | RC | 27th October
Proposal preparation & submission to BMMU by GPLF | YP,BLC,Krushi Mitra | 9th October
Fund release to cluster from GPLF | BPM,BLC | 25th October
Procurement of inputs with consultation with line department & Service Provider | Service Provider,BPM | 1st Fortnignt of November
MPR updation regarding Organic Cluster and share the details along with crop to SMMU | District Mis Person | 27th October
Field preparation & planting of saplings | Service Provider | 1st Fortnignt of November
Mid season Crop management Training | Service Provider | 1st Fortnignt of January

## Mushroom Cluster
Mushroom Production Cluster | Responsibility | Timelines
Training on Mushroom Cultivation with the help of KVKs, RSETII,line department | DPM,YP,RSETII | 21th September
Site selection for establishment of Mushroom shade | Krushi Mitra,BLC,BPM,YP | 23rd September
Sharing of SHG details with DMMU & SMMU | DPM,BPM,YP | 24th September
Proposal preparation & submission to BMMU by GPLF | MBK,BLC,BPM,YP | 27th September
Approval of proposal from line department for possible conververgence | BPM,YP | 28th September
MPR updation regarding Mushroom Cultivation Unit | District MIS person | 29th September
Fund release to cluster from GPLF | DPM,BPM | 30th September
Procurement of equipements as per guideline | MBK,BLC,BPM,YP | 5th October
Shade establishment & bed preparation | Krushi Mitra,BLC,BPM,YP | 11th October

## Honey Bee
Honey Bee Cultivation Unit | Responsibility | Timelines
Beneficiary selection for Bee colony management | Krushi Mitra,BLC,BPM,YP | 21th September
Site selection of Apiculture | Krushi Mitra,BLC,BPM,YP | 24th September
Sharing of SHG details with DMMU & SMMU | DPM,BPM,YP | 24th September
Training on Bee colony management with the help of KVKs, RSETII,line department | DPM,YP,RSETII | 29th September
Proposal preparation & submission to BMMU by GPLF | MBK,BLC | 1st October
Approval of proposal from line department for possible conververgence | BPM,YP | 5th October
MPR updation regarding Honey Bee Cultivation | District MIS person | 5th October
Fund release to cluster from GPLF | BPM | 11th October
Procurement of Bee box & other equipements as per guideline | Krushi Mitra,BLC,BPM,YP | 21st October
Bee box instalation | Krushi Mitra,BLC,BPM,YP | 25th October
Bee colony establishment | Krushi Mitra,BLC,BPM,YP | 25th October
First Harvest of Honey